Exhibit E: Required Bid Proposal Form.

Project: Dungeness River Nature Center Microgrid Resilience Project

Contractor/Company Name: _______________________________________

WA State Contractor License #: ___________________________________

SECTION 1: VENDOR / SUBCONTRACTOR DATA To comply with Department of Commerce reporting, please check all that apply to your business or your primary subcontractors: [ ] Minority-Owned Business [ ] Woman-Owned Business [ ] Veteran-Owned Business [ ] Small Business. If applicable please list your Certification #_______________.

SECTION 2A: LUMP SUM COST BREAKDOWN Please provide a cost for each component. The total of these line items must equal your Total Base Bid.

| Item | Scope of Work Category | Price |
| --- | --- | --- |
| 1 | Mobilization & General Conditions: Site prep, safety fencing, traffic control. | $__________ |
| 2 | Design, Engineering & Permitting: Final shop drawings, permit fees, utility paperwork. | $__________ |
| 3 | PV System Installation: 129.6 kW DC array, including roof-mounted modules, carport canopy structure arrays, optimizers, racking, wire management, and labor. | $__________ |
| 4 | BESS System Installation: 125 kW / 939 kWh BESS containers, rigging, placement, and labor. | $__________ |
| 5 | Civil & Structural Work: Trenching, minimum 8-inch-thick concrete pads, civil restoration. | $__________ |
| 6 | Electrical Balance of Systems: Conduit, AC aggregation panels, grid isolation device. | $__________ |
| 7 | Commissioning & Testing: Grid isolation testing, microgrid islanding simulation. | $__________ |
| 8 | Closeout, O&M, & Signage: As-built redlines, State CCA signage fabrication, staff training. | $__________ |
| 9 | Contingency / Force Account: The $70,000 Contingency / Force Account is reserved exclusively for truly unforeseen subsurface conditions (e.g., bedrock, unstable soils requiring over-excavation) approved in writing by the Owner. This contingency shall not be used to cover the repair of existing site utilities damaged during excavation if the contractor failed to perform the required Ground Penetrating Radar (GPR) scans prior to digging. | $ 70,000.00 |
|  | TOTAL BASE BID (Sum of Items 1 - 9): | $__________ |

SECTION 2B: ALTERNATES The Bidder shall provide separate pricing for the following Alternates. The Owner reserves the right to accept or reject any of these Alternates at their discretion.

| Alternate | Description | Price |
| --- | --- | --- |
| Alternate 1 | 5-Year Extended Warranty & Comprehensive Maintenance: Provide a comprehensive 5-year parts and labor warranty for the complete installed microgrid system, extending beyond the standard 1-year and 2-year workmanship guarantees required in the Base Bid. Additionally, provide a comprehensive 5-year system maintenance contract that includes, at a minimum, 6-month and 12-month system checks, testing, and preventive maintenance for all microgrid components. | $__________ |
| Alternate 2 | 10-Year Extended Warranty & Comprehensive Maintenance: Provide a comprehensive 10-year parts and labor warranty for the complete installed microgrid system. Additionally, provide a comprehensive 10-year system maintenance contract that includes, at a minimum, 6-month and 12-month system checks, testing, and preventive maintenance for all microgrid components. | $__________ |

SECTION 3: SCOPE & GRANT COMPLIANCE ACKNOWLEDGEMENTS Initial next to each item to confirm your bid complies with the RFP and State Grant conditions.

- _____ Contract and Specifications: I acknowledge that I have reviewed the Technical Specifications (Exhibit C1), Electrical Drawings (Exhibit C2), Structural Drawings (Exhibit C3), the sample Tribal Contract (01_Base_Contract_Agreement.docx), and the State Grant Terms (Exhibit A). My lump-sum price and provided Alternate bid pricing reflect the complete scope of work required by these documents.

- _____ Climate Commitment Act (CCA) Branding: I acknowledge that all site signage (pre, during, and permanent), project websites, and visible equipment decals must include the approved CCA logo and funding acknowledgment statement as dictated by the Department of Commerce.

- _____ Insurance & Additional Insureds: I confirm my ability to provide $1M General Liability, $1M Auto Liability, $1M Cyber Liability, $1M Professional Liability, and Fidelity Insurance, and I acknowledge that the State of Washington must be named as an additional insured.

- _____ Payment Terms & Invoicing: I understand that invoicing is strictly tied to the completion and acceptance of project milestones. While general 'advance payments' for unrendered services are prohibited, documented Equipment Deposits required by manufacturers to initiate production or secure delivery are allowable as defined project milestones. All individual expenses/materials over $50 require receipts for reimbursement.

- _____ Subcontracting: I acknowledge that all subcontractors must be approved in writing by the Department of Commerce prior to work commencing, and that subcontractors receiving $10,000 or more must secure Fidelity Insurance naming the Tribe as the beneficiary.

- _____ Utility Interconnection & Civil Restoration: I acknowledge utility coordination/testing, concrete pad pours (min. 8" thick), and "like and kind" civil restoration are fully included in my scope and price.

- _____ Private Utility Locates & GPR: I acknowledge that standard public utility locates (811) do not cover private property. As explicitly required by Note F on drawings E010 and E011, I confirm my bid includes the cost to hire a private utility locating service to perform Ground Penetrating Radar (GPR) scans prior to any excavation.

- _____ Future Generator Conduits: I acknowledge the scope includes trenching and installing the (2) 3-1/2" conduits from panel 2D1-EXT to the in-grade junction box for the future generator, as detailed on the site plan drawings, even though the generator equipment itself is Not In Contract.

- _____ Site Coordination & Facility Operations: I acknowledge that the Dungeness River Nature Center will remain operational during construction. I agree to maintain electrical, signal, and communication services to all functioning portions of the building throughout the project and will pre-arrange any necessary power outages with the Owner as required by Specification Section 26 05 00. I confirm that construction methods and conduit routing will be strictly coordinated with the Owner to minimize disruption to staff, visitors, existing EV chargers, and other Owner-specified areas as mandated in the Electrical Drawings. Furthermore, I acknowledge the requirement to coordinate and schedule all pre-study meetings, pre-installation meetings, and Microgrid Energy Management System (MEMS) testing dates in advance with the Facility Owner per Specification Sections 26 05 73, 26 31 00, 26 33 63.16, and 26 37 13.

- _____ Addenda: I acknowledge receipt of the following Addenda (List numbers): ____________________________________________________________.

SECTION 4: SIGNATURE I certify under penalty of perjury that the foregoing is true and correct, that I have reviewed the full design package and specifications, and that my bid contains no unstated exclusions.

Authorized Signatory (Print): _______________________________________

Signature (Electronic Signature Accepted): _______________________________________

Date: ______________

Title: _______________________________________